## ACQF Workplan 2025
ACQF NETWORK: WORKPLAN FOR THE PERIOD JANUARY 2025 TO SEPTEMBER 2025
| ACTIVITY | SUB ACTIVITY | Timelines | Status
Phase 1: January-September 2025. Focused on the organisation of the ACQF Network, fund raising and implementation of high-visibility activities for the members and international partners.
Phase 1:Jan 2025 - Sept 2025 | Start organisation of the ACQF Network: | Establish a multi-country Ad Hoc Team to start off the ACQF Network, define the roadmap and implementation plan and set-up a lean governance set-up. | 2025-04-01 | Done.Roadmap of Activities approved (22.01.25).TROIKA Presidency established (25.04.2025).
| Fund raising | Identify donor organisations / development partners towards continous promotion of the ACQF Network Activities. | Jan 2025 - Sept 2025 | Commenced. Held a virtual meeting with AUDA/NEPAD Team in June to explore possible areas of support.
| ACQF Implementation | Engage all the countries and regions and ensure participation in the ACQF Network activities including Referencing of NQFs to ACQF, RPL, CATs, and mapping of micro and digital credentials to the National Qualification Frameworks. | Jan 2025 - Sept 2025 | - Six countries are on course with Referencing of their respective NQFs to the African Continental Qualifications Framework (ACQF). - 4 countries – Mauritius, Seychelles, Mozambique and Kenya have initiated development of a Micro Credentials Framework and recognition of Micro Credentials.To be steered by the relevant Cluster.
| Governance | Hold a webinar to discuss and agree matters Network Registration & Internal Regulation (virtual);Create Technical Clusters | Jan 2025 - Sept 2025 | A webinar was held on 5th June 2025.Five Clusters were proposed and a call for nomination of members has been sent out. The following Clusters were proposed: Cluster 1: Referencing to ACQF and facilitation of recognition of qualifications Cluster 2: Qualifications and Credentials Platform (QCP) and digitalization Cluster 3: Research, development and implementation of NQF, RPL, CATS, Quality Assurance Cluster 4: Collaboration, communication and sharing Cluster 5: Financing and fund raising to support sustainability and impact-oriented actions Network registration will be discussed and considered during the physical meeting to be held in Johannesburg in July 2025.
| Promotion and awareness creation | Hold webinars with members and partner organisations, AUC, EU institutions and global networks | Jan 2025 - Sept 2025 | -Held a Webinar of the ACQF Network on 5 June -Held a virtual meeting with AUDA/NEPAD Team in June to explore possible areas of support.
| Enhance Digital Presence | Update the ACQF website, introduce new web pages and resources for the ACQF Network | Jan 2025 - Sept 2025 | - The ACQF Network Website has been duly updated with new information. - A Cluster has been created to look at Collaboration, Communication and Sharing, and will oversee management of the ACQF Network Website in collaboration with ETF.
| Research | Undertake common research and review of the impact, challenges and successes of implementation of National, Regional and Continental qualifications Framework; alignment and comparibility of qualifications. | Jan 2025 - Sept 2025 | The Terms of Reference for the research task are under development as we await the finalization of the constitution of Cluster 3: Research, development and implementation of NQF, RPL, CATS, Quality Assurance.
| Annual Conference I (physical} | Organise an annual conference on Qualification Frameworks to review progress, share good practices and resources, discuss challenges, and plan for future initiatives; for purposes of reporting, peer-learning, dissemination of best practices and trust building. | Sept 2025 | Deliverable under implementation but may not be concluded within the contract period due to delay in commencement of the research study.
Phase 2: Build capacities and create awareness of member countries; and for various stakeholders
Phase 2: Oct 2025 - Dec 2025 | Promote Skills Development, Qualifications and Credentials: | Promote Skills Development, Qualifications and Credentials: Launch campaigns and communication to emphasise the importance of skills, and qualifications and credentials for development, social inclusion, growth and innovation. | Jan 2025 - Dec 2025 | - I June 2025, Consultative meetings were held between ETF and all the 6 countries that are participating in piloting of the Qualifications Credentials Platform (QCP) - Communications and advocacy cluster has been created to work on the promotion aspect.
| Annual Conference II (Physical) | Employer Engagement: Focus on employer; Foster trust and ensure continuous feedback from the private sector on labour market trends and demand for skills, and qualifications and credentials. | Oct 2025 - Dec 2025 | Subject to availability of Resources
Labour Market Intelligence System: work towards development of a system for labour market monitoring, analysis and a users’ visualisation platform.
| Communication, Outreach and Reporting | Plan and execute outreach activities and define national focal points for smooth communication. | Jan 2025 - Dec 2025 | Collaboration, Communication and Sharing Cluster was proposed and will be constituted during the July meeting in South Africa where TORs will also be finalised.