## Slide 1
PROGRESS REPORT
Cluster 1- Referencing to ACQF And Facilitation of Recognition of Qualifications
Presented by: The Secretariat, Cluster 1
Alberto Landim
October 1, 2025 Caudan Arts Centre, Port Louis, Mauritius
Referencing
NQF
Support
The 6th ACQF Continental Forum

## Slide 2
Cluster 1 Key Progress Achieved
Terms of Reference (ToRs) Finalized: The Cluster conducted a final review and approved revisions to the ToRs, incorporating all member contributions.
Mandate Clarified: Agreed to explicitly link referencing and recognition, highlighting that referencing facilitates the transparency and comparability required for. recognition.
Duration Proposed: It was proposed to extend the Cluster's mandate until the end of 2026, aligning with the ACQF II project timeline.

## Slide 3
Cluster 1 Next Steps and Priorities
Finalize de draft of the Action Plan 2025-2026: linking the priority areas in the action plan to the terms of reference for clarity.
Referencing Focus: Make it a major focus to encourage and support countries to complete their referencing process
Convention Support: Add action points to assist countries in ratifying the Addis and Global Conventions on recognition, utilizing the relevant ACQF Technical Note document
Mandate Confirmation: Consultation must occur with ACQF leadership regarding the proposed extension of the Cluster’s mandate to the end of 2026

## Slide 4
Survey: Referencing to ACQF and Implementation of NQFs
Survey period
Focus on:
19
Countries Surveyed
September 23 to September 30, 2025
NQF to ACQF referencing process;
NQF implementation/establishment;
Technical assistance needs;
Member Countries’ views, ideas, and suggestions on enhancing Cluster 1 activities and NQF Referencing.

## Slide 5
NQF to ACQF Referencing - Awareness Levels
1. Awareness of NQF–ACQF Referencing
Fully Understand (5)
Cabo Verde
Ethiopia
Aware, but need more information and support (8)
Cluster 1 Progress Report | 2025-10-01
Eswatini
Kenya
Malawi
Angola
Botswana
Lesotho
Seychelles
Mauritius
Zambia
Zimbabwe
Mozambique
Aware, but NQF not Approved (4)
Cameroon
Guinea-Bissau
Democratic Republic of Congo
Senegal

## Slide 6
Awareness of the ACQF Referencing Guidelines and
support materials on the website
Countries by awareness level
Fully Informed (8)
Aware, but need Information/support (8)
Not Informed (3)
Cabo Verde
Eswatini
Ethiopia
Kenya
Leshoto
Seychelles
Zambia
Sierra Leone
Angola
Cameroon
Malawi
DR Congo
Mauritius
Tunisia
Zimbabwe
Mozambique
Botswana
Guinea-Bissau
Senegal

## Slide 7
Referencing NQF to ACQF - Interest & Readiness
Countries by Interest Level
11
5
2
1
Interested in Referencing
Interested, but need sometime to prepare
Pilot Referencing Process started
Concluded the referencing report

## Slide 8
Referencing to the ACQF - Interest & Readiness
Interested Countries
Angola
Botswana
Cabo Verde
Interested, but needs some time to Prepare
Cameroon
Guinea-Bissau
Malawi
Mauritius
Tunisia
Zambia
Sierra Leone
Ethiopia
Pilot Referencing Process started
Leshoto
DR Congo
Senegal
Mozambique
Eswatini
Seychelles
Concluded the referencing report
Kenya

## Slide 9
Referencing to the ACQF - Current Status
3
1
8
1
4
Report completed
Near completion
Drafting
National Referencing
Team not fully organized
Not started
1
1
Needs Technical support
NQF not operational

## Slide 10
Referencing to the ACQF - Timeline Projections
Timeline Analysis
Early submissions (2025)
9 countries plan to submit complete draft referencing reports by the end of 2025
Later submissions (2026)
9 countries plan to submit complete draft referencing reports by the end of 2026
Delayed start
1 country (Botswana) has not yet started and needs capacity building and technical support
Cluster support planning
Timeline projections help identify when targeted support is needed for countries facing delays
Implications for Cluster Activities
Based on the timeline projections, Cluster 1 can prioritize providing targeted support to the 11 countries that will submit drafts in 2025, while also maintaining capacity to assist the 10 countries planning 2026 submissions. Special attention is needed for Botswana, which has not yet started the process.
Cluster 1 Progress Report | 2025-10-01

## Slide 11
Implementation of NQFs
NQF Implementation Status
Cluster 1 Progress Report | 2025-10-01
NQF in Active Development
14
NQF well established and Reviewed
Seychelles
NQF currently being implemented
Senegal
NQF under Revision to address Gaps
Zambia
Awainting approval by the Council of Ministers
Guinea-Bissau
Democratic Republic of Congo
No current plans
Angola
Botswana
Cabo Verde
Cameroon
Eswatini
Ethiopia
Kenya
Leshoto
Malawi
Mauritius
Mozambique
Sierra Leone
Zimbabwe
Tunisia

## Slide 12
Key Insights
Majority of countries (14) are actively developing their NQFs
Some countries face delays in implementation (Zambia needs to address gaps)
Guinea-Bissau and DR Congo need urgent support to establish their frameworks
Implementation of NQFs

## Slide 13
Technical Assistance Needs - Overview
Categories of Needs
Organization Support
Route maps, roles and responsibilities for referencing process
Team Building
Support for establishing and strengthening national referencing teams
Training
Comprehensive training plans on referencing standards and processes
Report Drafting
Support for drafting, finalizing and submitting reference reports
Peer Review
Finding suitable peers for report review and validation

## Slide 14
Needs Distribution
Technical Assistance Needs - Overview
Organization Support
Trainning on Referencing Standards
Team building
Report drafting
Report finalization
Peer Review

## Slide 15
Organization support is the most requested need
Training on referencing standards is highly requested
Report drafting and finalization support are common needs
All countries expressed needs for different stages of the referencing process
Cluster 1 Progress Report | 2025-10-01
Technical Assistance Needs - Overview
Key Insights

## Slide 16
Based on the survey data, the following countries require immediate intervention due to significant challenges in their NQF implementation and referencing processes.
GB
Guinea-Bissau
Highest Urgency
The NQF has not yet been approved by the Council of Ministers.
Lack of familiarity with the ACQF reference guide and supporting materials
Technical support is required to establish a reference team
CD
DR Congo
High Urgency
There are currently no NQF program
Need more information and support
Support is needed starting from the foundational level
BW
Botswana
Medium-High Urgency
Lack of familiarity with the ACQF reference guide and supporting materials
The reference process has not yet started.
Requires capacity building and technical support
Malawi
Medium Urgency
The NQF has not yet been implemented
Need more information and support
Issues with NQF operation must be resolved before advancing the reference
Common Urgent Support Needs:
Legislative approval support
Basic information provision
Technical team building
Training on standards
Cluster 1 Progress Report | 2025-10-01
Countries Requiring Urgent Support

## Slide 17
Specific Enhancement Ideas and Suggestions from Member Countries
Member countries proposed concrete and actionable ideas to strengthen Cluster 1 activities and the NQF referencing process
Targeted Workshops
Workshops on report writing, methodology application, and quality assurance processes for specific NQF referencing aspects.
Digital Repository
Centralized online platform for NQF documents, best practices, and referencing reports to facilitate knowledge sharing.
Mentorship Program
Pairing countries at different stages of NQF development to foster peer-to-peer learning and provide tailored guidance.
Standardized Templates
Standard templates for NQF referencing reports and other documents to ensure consistency and ease of comparison.
Expert Missions
On-site technical assistance and guidance during critical phases of NQF development and referencing.
Communication Channels
Regular newsletters, dedicated online forums, and virtual meetings to improve information flow and engagement.

## Slide 18
Conclusions - Progress Overview
Overall Progress Status
Most countries show active interest in ACQF referencing
Knowledge levels have improved in many countries
Most countries are developing or implementing NQFs
ACQF Referencing Awareness
5 countries fully aware
8 need more info
4 no NQF approved
NQF Implementation
14 active development
1 established
1 implementing
Collective Achievements
Complete Referencing Reports
Kenya has completed report
Cape Verde has completed and considered improvements
Pilot Referencing
Eswatini and Seychelles have started pilot processes
Upcoming Submissions
9 countries plan to submit drafts by end of 2025
10 countries plan to submit by end of 2026
Main Challenges
Knowledge Gaps
Some countries lack understanding of ACQF guidelines
NQF Barriers
Guinea-Bissau, Malawi: NQF not approved
Congo DR: No NQF plan
Technical Assistance Needs
Organization support, team building, training
Report drafting and finalization support
Urgent Support Needed
4 countries require immediate assistance
Cluster 1 Progress Report | 2025-10-01